## Sheet1
Phases | Status | Code | Pre. | Major Tasks | Elements | Details | Team Member | Start Date | Start Hour | Duration | Due | Notes
Planning | Completed | 100 | n/a | Finalizing the Template Design | Screen Size | [5 empty] | 2017-01-13 | Width: 1024, Height: 768 for Main Elements
| In-Progress | 110 |  |  | Logo | Image and size | Gregor | 2017-01-13 |  |  | 2017-01-14
|  | 120 |  |  | Header | Image and size | Gregor | 2017-01-13 |  |  | 2017-01-14
|  | 122 |  |  | Scroll for Banner | Image 1004x200 | Mehran | 2017-01-13 |  |  | 2017-01-14
[5 empty] | Scroll for Banner | Left Side Cut-off | Mehran
|  | 130 |  |  | Tool Bar | Image and size | Mehran | 2017-01-18 |  |  | 2017-01-12
|  | 135 |  |  | Tool Bar Graphics to Google | All seperate images for Tool Br | Mehran | 2017-01-13 |  |  | 2017-01-14
|  | 140 |  |  | Nav Bar | Image and size
|  | 150 |  |  | Images | Home Page
|  | TBD |  |  | Images | Page #1
|  | TBD |  |  | Images | Page #2
|  | ... |  | ... | ... | ...
|  | 180 |  |  | Images | Page #n
|  | 190 |  | Preparing Final Image Files | images | Final format all sizes | Mehran | 2017-01-21 |  |  | 2017-01-23
Website |  |  |  | Coding | Home Page and Main Elements |  | Gregor | 2017-01-14 |  |  | 2017-01-15
Page #1
Page #2
Page#n
Collecting and Combining Parts
Testing
Fixing Bugs
Testing
Putting the Website on Hosting
Final Test
Presentation |  |  |  | Preparing Materials
Making PowerPoint File
Group Review of PowerPoint
PowerPoint Update and Finalize
|  |  |  | Preparing Speech |  |  |  | TBD | TBD | TBD | 2017-01-22
|  |  |  | Practicing the Presentation |  |  |  | 2017-01-23 | 12:30 | TBD | 2017-01-23